## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Website release | Elie .A | 2020-06-06 | 2020-07-13 |  | 90% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Build DataBase |  | Elie .A |  | 2020-06-06 | 2020-06-18 | 12 | Complete
| Design tables and relations |  | Haitham .B |  | 2020-06-06 | 2020-06-12 | 6 | Complete
| create tables and user |  | Haitham .B |  | 2020-06-12 | 2020-06-16 | 4 | Complete
| add values to the tables |  | Maisa .A |  | 2020-06-16 | 2020-06-18 | 2 | Complete
| Build the frontend |  | Hala .A |  | 2020-06-20 | 2020-06-28 | 8 | Complete
| Design the web pages |  | Maisa .A |  | 2020-06-20 | 2020-06-24 | 4 | Complete
| implements interfaces for the services |  | Haitham .B |  | 2020-06-24 | 2020-06-28 | 4 | Complete
| Design interfaces for admin edittingsSprint 3 |  | Haitham .B |  | 2020-06-30 | 2020-07-13 | 13 | In Progress
| design interface for servic managing |  | Elie .A |  | 2020-06-30 | 2020-07-04 | 4 | Complete
| design interface for users managing |  | Maisa .A |  | 2020-07-04 | 2020-07-09 | 5 | In Progress
| design interface for site monitoring |  | Hala .A |  | 2020-07-09 | 2020-07-13 | 4 | Not Started